## Team Members
Enter the First Name of Each Team Member | HOW TO USE: | 1. File Menu --> Make a copy
Eric |  | 2. Save to one team member's Google drive
Gaurav |  | 3. Share file with other team members
Scott |  | 4. Edit First Names on this tab
Oscar |  | 5. Add your team name to the name of this document
6. For each sprint, duplicate the sprint template and change the start date
DOCUMENT HISTORY
| 2017-09-20 | Created by Justin Sybrandt (http://sybrandt.com/post/google-slides-agile/)
| 2019-03-23 | Modified by Susanne Sherba for use in COMP 3381 (Software Engineering I)

## Product Backlog
Sprint Number | User Story ID | User Story Title | Brief Description | Additional Information | Priority | Status
| S1 | Create Account | As a user, I want to create an account, so that I can login to store information in the future |  | 1-high | Done
| S2 | Login | As a user, I want to login to my account, so that store and view my information |  | 1-high | Done
| S3 | Store information | As a user, I want to store information of the volunteer/paid/credit or any other work, so that I can view them in the future | This can consist data like activity category, activity type, Start - End dates, Number of hours, Organization/Department, Contact Name/Title/other info, Activity Summary, Additional details like skills learned or developed | 1-high | Done
| S4 | View Information | As a user, I want to view the information stored in my account, so that I can edit/delete information |  | 1-high | Done
| S5 | Edit Information | As a user, I must be able to edit the information stored by me, so that i can make changes to the information if needed. |  | 1-high | In Progress
| S6 | Delete Information | As a user, I must be able to delete the information, so that I can remove information i do not need |  | 1-high | In Progress
| S7 | Upload Files | As a user, I must be able to upload any files (like images, docs,pdfs), so that i can view them later |  | 3-low | To Do
| S8 | Print information | As a user, I must be able to print out information from my account as a summary ,so that i can have a physical copy of the work I did |  | 3-low | To Do
| S9 | Change Password | As a user, I want to change my password so I can log into my account if I forget my password |  | 3-low | In Progress
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 1-high | To Do
[5 empty] | 2-medium | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do

## Sprint 1
User Story ID | Sub Story | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
S1 |  | As a user, I would like to store information in the application | 10 |  |  | To Do |  | Sprint Number: | 0 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2020-04-22 | 0 | 0 | 18 | 18
| S1 - 1 | As a developer, I would like to have a basic interface of the applcation |  |  |  | To Do |  | Start Date: | 2020-04-22 | Eric | 3 | 0 | 0% | 2020-04-23 | 0 | 0 | 18 | 15.4286
| S1 - 2 | As a developer, I would like to have forms to enter information | 3 |  |  | To Do |  | Sprint Length | 14 | Gaurav | 15 | 9 | 60% | 2020-04-24 | 0 | 0 | 18 | 12.8571
| S1 - 3 | As a developer, I would like to store the information temporarily so that I can acess it later |  |  |  | To Do |  | Hours Per Day: | 2.5714 | Scott | 0 | 0 | 0% | 2020-04-25 | 0 | 0 | 18 | 10.2857
| S1 - 4 | As a developer, I would like to have forms for all the basic information suggested by the sponsor |  |  |  | To Do
S2 |  | As a user, I would like to view information in the application | 5 |  |  | To Do |  |  |  | Oscar | 0 | 0 | 0% | 2020-04-26 | 0 | 0 | 18 | 7.7143
| S2- 1 | As a developer, I would like to view the information stored. | 5 | 4 | Gaurav | In Progress |  |  |  |  | 0 | 0 | 0% | 2020-04-27 | 0 | 0 | 18 | 5.1429
| S2 - 2 | As a developer, I would like to show the information stored back to the user |  |  | Oscar | In Progress |  |  |  |  | 0 | 0 | 0% | 2020-04-28 | 0 | 0 | 18 | 2.5714
| S2 - 3 | As a developer, I would like the user to be able to log into the website to view stored information | 3 | 1 | Eric | In Progress | [7 empty] | 2020-04-29 | 0 | 0 | 18 | 0
[6 empty] | To Do |  |  |  | Total: | 18 | 9 | 50% | 2020-04-30 | 0 | 0 | 18 | 0
[6 empty] | To Do | [7 empty] | 2020-05-01 | 0 | 0 | 18 | 0
S3 |  | As a developer, I would like to learn how to code in Angular |  | 6.5 | Eric | In Progress | [7 empty] | 2020-05-02 | 0 | 0 | 18 | 0
S3 |  | As a developer, I would like to learn how to code in Angular | 10 | 5 | Gaurav | In Progress | [7 empty] | 2020-05-03 | 0 | 0 | 18 | 0
[6 empty] | To Do | [7 empty] | 2020-05-04 | 0 | 0 | 18 | 0
[6 empty] | To Do | [7 empty] | 2020-05-05 | 0 | 0 | 18 | 0
[6 empty] | To Do | [7 empty] | 2020-05-06 | 0 | 0 | 18 | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Chart Dates = if(and(ISDATE([Chart Dates, row above]),[Chart Dates, row above]-K3<K4), [Chart Dates, row above]+1, "")
Current Remaining Work = if([Chart Dates] <= TODAY(), N11-[Current Completed Work], "")

## Sprint 2
| Sub Story | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
S1 |  | As a user, I would like to store information in the application |  |  |  | To Do |  | Sprint Number: | 0 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2020-05-06 | 3 | 3 | 27 | 30
| S1 - 1 | As a developer, I would like to have a basic interface of the applcation | 3 | 3 | Oscar | Done | 2020-05-06 | Start Date: | 2020-05-06 | Eric | 9 | 2 | 22.22% | 2020-05-07 | 0 | 3 | 27 | 27.8571
| S1 - 2 | As a developer, I would like to have forms to enter information | 3 | 1 | Eric | In Progress |  | Sprint Length | 14 | Gaurav | 10 | 9 | 90% | 2020-05-08 | 0 | 3 | 27 | 25.7143
| S1 - 3 | As a developer, I would like to store the information temporarily so that I can acess it later |  |  |  | To Do |  | Hours Per Day: | 2.1429 | Scott | 0 | 0 | 0% | 2020-05-09 | 0 | 3 | 27 | 23.5714
| S1 - 4 | As a developer, I would like to have forms for all the basic information suggested by the sponsor |  |  |  | To Do |  |  |  | Oscar | 11 | 3 | 27.27% | 2020-05-10 | 0 | 3 | 27 | 21.4286
S2 |  | As a user, I would like to view information in the application |  |  |  | To Do |  |  |  |  | 0 | 0 | 0% | 2020-05-11 | 0 | 3 | 27 | 19.2857
| S2- 1 | As a developer, I would like to view the information stored. | 1 | 1 | Gaurav | In Progress |  |  |  |  | 0 | 0 | 0% | 2020-05-12 | 0 | 3 | 27 | 17.1429
| S2 - 2 | As a developer, I would like to show the information stored back to the user | 3 | 2 | Oscar | In Progress | [7 empty] | 2020-05-13 | 0 | 3 | 27 | 15
| S2 - 3 | As a developer, I would like the user to be able to log into the website to view stored information | 2 | 2 | Eric | Done | 2020-05-19 |  |  | Total: | 30 | 14 | 46.67% | 2020-05-14 | 0 | 3 | 27 | 12.8571
S3 | S3-1 | As a developer, I would like to have the basic functionality of the springboot server(Add,Edit and Delete) | 4 | 4 | Gaurav | Done | 2020-05-18 | [6 empty] | 2020-05-15 | 0 | 3 | 27 | 10.7143
| S3-2 | As a developer, I would like to have the pages and the server connected | 5 |  | Oscar | In Progress | [7 empty] | 2020-05-16 | 0 | 3 | 27 | 8.5714
S4 |  | As a developer, I would like to learn how to code in Angular | 4 | 2 | Eric | In Progress | [7 empty] | 2020-05-17 | 5 | 8 | 22 | 6.4286
S4 |  | As a developer, I would like to learn the basics of creating springboot server | 5 | 6 | Gaurav | Done | 2020-05-17 | [6 empty] | 2020-05-18 | 4 | 12 | 18 | 4.2857
[6 empty] | To Do | [7 empty] | 2020-05-19 | 2 | 14 | 16 | 2.1429
[6 empty] | To Do | [7 empty] | 2020-05-20 | 0 | 14 | 16 | 0
[6 empty] | To Do | [8 empty] | 0 | 11 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 11 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 11 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 11 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 11 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 11 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 11 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 11 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 11 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 11 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 11 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 6 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 2 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[6 empty] | To Do | [8 empty] | 0 | 0 |  | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Chart Dates = if(and(ISDATE([Chart Dates, row above]),[Chart Dates, row above]-K3<K4), [Chart Dates, row above]+1, "")
Current Remaining Work = if([Chart Dates] <= TODAY(), N10-[Current Completed Work], "")

## Sprint 3
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
S1 | As a user, I would like to have forms to enter information | 3 | 3 | Eric | Done | 2020-05-28 | Sprint Number: | 0 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2020-05-20 | 3 | 3 | 26 | 29
S2 | As a user, I would to view the about me page for more information | 3 |  | Scott | Done |  | Start Date: | 2020-05-20 | Eric | 4 | 4 | 100% | 2020-05-21 | 0 | 3 | 26 | 26.9286
S3 | As a developer, I would like to use data binding to pull user entered information from the website | 1 | 1 | Eric | Done | 2020-06-03 | Sprint Length | 14 | Gaurav | 8 | 8 | 100% | 2020-05-22 | 0 | 3 | 26 | 24.8571
S4 | As a developer, I would like to learn the basics of creating springboot server and working with Postman to test the temporary server | 5 | 5 | Gaurav | Done | 2020-05-30 | Hours Per Day: | 2.0714 | Scott | 9 | 9 | 100% | 2020-05-23 | 0 | 3 | 26 | 22.7857
S5 | As a developer I would like to allow to user to view the added information | 6 |  | Scott | Done |  |  |  | Oscar | 8 | 8 | 100% | 2020-05-24 | 0 | 3 | 26 | 20.7143
S6 | As a developer, I would like to update the JSON file format in the spring boot server so that it can take in array of events | 3 | 5 | Gaurav | Done | 2020-06-01 |  |  |  | 0 | 0 | 0% | 2020-05-25 | 0 | 3 | 26 | 18.6429
S7 | As a user, i would like to be able to navigate through pages using a navbar and homepage. | 2 | 2 | Oscar | Done | 2020-05-20 |  |  |  | 0 | 0 | 0% | 2020-05-26 | 1 | 4 | 25 | 16.5714
S8 | As a developer, i would like to have an angular service to easily connect components to the database. | 4 | 4 | Oscar | Done | 2020-05-27 | [6 empty] | 2020-05-27 | 4 | 8 | 21 | 14.5
S9 | As a developer, I would like to have a routing module to connect urls to component html templates. | 1 | 1 | Oscar | Done | 2020-05-20 |  |  | Total: | 29 | 29 | 100% | 2020-05-28 | 3 | 11 | 18 | 12.4286
S10 | As a developer, I would like to have a data model to follow in angular to send to the springboot server. | 1 | 1 | Oscar | Done | 2020-05-26 | [6 empty] | 2020-05-29 | 0 | 11 | 18 | 10.3571
[5 empty] | To Do | [7 empty] | 2020-05-30 | 5 | 16 | 13 | 8.2857
[5 empty] | To Do | [7 empty] | 2020-05-31 | 0 | 16 | 13 | 6.2143
[5 empty] | To Do | [7 empty] | 2020-06-01 | 3 | 19 | 10 | 4.1429
[5 empty] | To Do | [7 empty] | 2020-06-02 | 0 | 19 | 10 | 2.0714
[5 empty] | To Do | [7 empty] | 2020-06-03 | 1 | 20 | 9 | 0
[5 empty] | To Do | [8 empty] | 9 | 26 |  | 0
[5 empty] | To Do | [8 empty] | 9 | 35 |  | 0
[5 empty] | To Do | [8 empty] | 9 | 44 |  | 0
[5 empty] | To Do | [8 empty] | 9 | 53 |  | 0
[5 empty] | To Do | [8 empty] | 9 | 62 |  | 0
[5 empty] | To Do | [8 empty] | 9 | 71 |  | 0
[5 empty] | To Do | [8 empty] | 9 | 79 |  | 0
[5 empty] | To Do | [8 empty] | 9 | 84 |  | 0
[5 empty] | To Do | [8 empty] | 9 | 90 |  | 0
[5 empty] | To Do | [8 empty] | 9 | 99 |  | 0
[5 empty] | To Do | [8 empty] | 9 | 103 |  | 0
[5 empty] | To Do | [8 empty] | 9 | 112 |  | 0
[5 empty] | To Do | [8 empty] | 9 | 118 |  | 0
[5 empty] | To Do | [8 empty] | 9 | 127 |  | 0
[5 empty] | To Do | [8 empty] | 9 | 135 |  | 0
[5 empty] | To Do | [8 empty] | 9 | 135 |  | 0
[5 empty] | To Do | [8 empty] | 9 | 135 |  | 0
[5 empty] | To Do | [8 empty] | 9 | 135 |  | 0
[5 empty] | To Do | [8 empty] | 9 | 135 |  | 0
[5 empty] | To Do | [8 empty] | 9 | 135 |  | 0
[5 empty] | To Do | [8 empty] | 9 | 135 |  | 0
[5 empty] | To Do | [8 empty] | 9 | 135 |  | 0
[5 empty] | To Do | [8 empty] | 9 | 135 |  | 0
[5 empty] | To Do | [8 empty] | 9 | 135 |  | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Chart Dates = if(and(ISDATE([Chart Dates, row above]),[Chart Dates, row above]-J3<J4), [Chart Dates, row above]+1, "")
Current Remaining Work = if([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")

## Sprint 4
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
S1 | As a developer, I would the enter info page to send data to the database | 3 | 3 | Eric | Done | 2020-06-07 | Sprint Number: | 4 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2020-06-03 | 0 | 0 | 28.5 | 28.5
S2 | As a user, I would like to have a home page to look at | 2 | 2 | Eric | Done | 2020-06-09 | Start Date: | 2020-06-03 | Eric | 5 | 5 | 100% | 2020-06-04 | 0 | 0 | 28.5 | 26.4643
S3 | As a developer, I would like to have the springboot backend send and receive events to add to the database | 2 | 2 | Gaurav | Done | 2020-06-09 | Sprint Length | 14 | Gaurav | 4 | 4 | 100% | 2020-06-05 | 0 | 0 | 28.5 | 24.4286
S4 | As a developer, I would like to update the JSON format for PUT request to add new events to existing users | 1 | 1 | Gaurav | Done | 2020-06-09 | Hours Per Day: | 2.0357 | Scott | 9.5 | 9.5 | 100% | 2020-06-06 | 5 | 5 | 23.5 | 22.3929
S5 | As a developer, I would like to update the existing user by adding the new event sent by the user | 1 | 1 | Gaurav | Done | 2020-06-09 |  |  | Oscar | 10 | 10 | 100% | 2020-06-07 | 3 | 8 | 20.5 | 20.3571
S6 | As a user I would like to be able to export the info from the table in the about page into a downloadable csv | 5 | 5 | Scott | Done | 2020-06-10 |  |  |  | 0 | 0 | 0% | 2020-06-08 | 1 | 9 | 19.5 | 18.3214
S7 | As a user i would like to be able to sort and filter entries in the table of entries on the about page | 4 | 4 | Scott | Done | 2020-06-09 |  |  |  | 0 | 0 | 0% | 2020-06-09 | 12 | 21 | 7.5 | 16.2857
S8 | As a developer I would like to have comments in the about page code so that it is clear what the purpose of each method is to make future development easier | 0.5 | 0.5 | Scott | Done | 2020-06-11 | [6 empty] | 2020-06-10 | 5 | 26 | 2.5 | 14.25
S9 | As a developer I would like to have different service methods, for put, post, and get requests. | 5 | 5 | Oscar | Done | 2020-06-06 |  |  | Total: | 28.5 | 28.5 | 100% | 2020-06-11 | 2.5 | 28.5 | 0 | 12.2143
S10 | As a user, I would like to register as a user. | 1 | 1 | Oscar | Done | 2020-06-08 | [6 empty] | 2020-06-12 | 0 | 28.5 |  | 10.1786
S11 | As a user, i would like to see the information I entered in the About page. | 2 | 2 | Oscar | Done | 2020-06-09 | [6 empty] | 2020-06-13 | 0 | 28.5 |  | 8.1429
S12 | As a developer, I would like to have specific service methods to be able to register and login. | 2 | 2 | Oscar | Done | 2020-06-11 | [6 empty] | 2020-06-14 | 0 | 28.5 |  | 6.1071
[5 empty] | To Do | [7 empty] | 2020-06-15 | 0 | 28.5 |  | 4.0714
[5 empty] | To Do | [7 empty] | 2020-06-16 | 0 | 28.5 |  | 2.0357
[5 empty] | To Do | [7 empty] | 2020-06-17 | 0 | 28.5 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 28.5 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 28.5 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 28.5 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 23.5 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 20.5 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 19.5 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 7.5 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 2.5 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Chart Dates = if(and(ISDATE([Chart Dates, row above]),[Chart Dates, row above]-J3<J4), [Chart Dates, row above]+1, "")
Current Remaining Work = if([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")

## Sprint Template (Make a copy!)
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
S1 | Brief description |  |  |  | To Do |  | Sprint Number: | 0 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2019-03-30 | 0 | 0 | 0 | 0
[5 empty] | To Do |  | Start Date: | 2019-03-30 | Eric | 0 | 0 | 0% | 2019-03-31 | 0 | 0 | 0 | 0
[5 empty] | To Do |  | Sprint Length | 14 | Gaurav | 0 | 0 | 0% | 2019-04-01 | 0 | 0 | 0 | 0
[5 empty] | To Do |  | Hours Per Day: | 0 | Scott | 0 | 0 | 0% | 2019-04-02 | 0 | 0 | 0 | 0
[5 empty] | To Do |  |  |  | Oscar | 0 | 0 | 0% | 2019-04-03 | 0 | 0 | 0 | 0
[5 empty] | To Do |  |  |  |  | 0 | 0 | 0% | 2019-04-04 | 0 | 0 | 0 | 0
[5 empty] | To Do |  |  |  |  | 0 | 0 | 0% | 2019-04-05 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-06 | 0 | 0 | 0 | 0
[5 empty] | To Do |  |  |  | Total: | 0 | 0 | 0% | 2019-04-07 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-08 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-09 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-10 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-11 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-12 | 0 | 0 | 0 | 0
[5 empty] | To Do | [7 empty] | 2019-04-13 | 0 | 0 | 0 | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
[5 empty] | To Do | [8 empty] | 0 | 0 |  | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Chart Dates = if(and(ISDATE([Chart Dates, row above]),[Chart Dates, row above]-J3<J4), [Chart Dates, row above]+1, "")
Current Remaining Work = if([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")